{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["汇总表","18年高效节水灌溉土建及安装清单"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"汇总表","index":0,"n_rows":14,"n_cols":4,"rows_kept":14,"merged":[[0,0,0,3],[9,0,9,1],[11,0,11,1],[12,0,12,1],[13,1,13,2]],"flags":["formulas_cached_only"]}
["新沂市2018年新增千亿斤粮食产能规划田间工程末级渠系项目\n投标报价汇总表"]
["组号","分组名称","合计（元）","备注"]
["一","土方工程"]
["二","管道安装工程"]
["三","管件及其他材料购置与安装工程"]
["四","机电设备购置及安装工程"]
["五","临时工程"]
["六","安全文明措施费",{"v":20000,"d":"20000.00"}]
["七","备用金",{"v":30000,"d":"30000.00"}]
["合计=一至七项之和"]
[]
["投标人：",null,null,"(盖章)"]
["法定代表人或委托代理人：",null,null,"(签字)"]
[null,"             年             月             日"]

{"sheet":"18年高效节水灌溉土建及安装清单","index":1,"n_rows":76,"n_cols":7,"rows_kept":76,"merged":[[0,0,0,6],[71,0,71,2],[73,0,73,2],[73,3,73,5],[74,0,74,2],[75,3,75,5]],"flags":["formulas_cached_only"]}
["新沂市2018年中央高效节水灌溉补助资金项目A标段（土建及安装工程）\n工程量清单"]
["序号","项目名称","单位","数量","单价（元）","合价（元）","备注"]
["一","土方工程"]
[1,"土方开挖","m3",{"v":17439,"d":"17439.00"}]
[2,"土方回填压实","m3",{"v":15550,"d":"15550.00"}]
[3,"管道细土回填压实","m3",{"v":1787.4,"d":"1787.40"}]
["二","管道安装工程"]
[1,"PVC-U塑料管 管径DN90mm 0.8Mpa","m",{"v":3390,"d":"3390.00"}]
[2,"PVC-U塑料管 管径DN110mm 0.8Mpa","m",{"v":1020,"d":"1020.00"}]
[3,"PVC-U塑料管 管径DN63mm 0.8Mpa","m",{"v":13825,"d":"13825.00"}]
[4,"出地管(DN50mmPE100管) 0.8Mpa","m",{"v":1218,"d":"1218.00"}]
[5,"DN32出地管（PE100 0.8Mpa）","m",{"v":1485,"d":"1485.00"}]
[6,"PE100辅管(DN50mm) 0.8Mpa","m",{"v":11620,"d":"11620.00"}]
[7,"PE100毛管(DN25mm) 0.8Mpa","m",{"v":276650,"d":"276650.00"}]
[8,"PE100毛管(DN4mm)","m",{"v":138325,"d":"138325.00"}]
["三","管件及其他材料购置与安装工程"]
[1,"Φ30cm灌溉井成井","m",{"v":80,"d":"80.00"}]
[2,"井房","m2",{"v":13.8,"d":"13.80"}]
[3,"液位传感器","套",15]
[4,"扬水管","m",{"v":1200,"d":"1200.00"}]
[5,"0.4级1.6Mpa压力表压力表","块",30]
[6,"可拆卸螺翼式干式冷水表","块",32]
[7,"DN100mm微阻缓闭止回阀","个",12]
[8,"DN125mm微阻缓闭止回阀","个",3]
[9,"2\"进排气阀","个",30]
[10,"机房照明（15个井房）","项",1]
[11,"防雷接电（15个井房）","项",1]
[12,"PVC-U异径三通(DN90-63mm) ","个",42]
[13,"PVC-U异径三通(DN110-63mm) ","个",18]
[14,"PVC-U正三通(DN90mm) ","个",11]
[15,"PVC-U正三通(DN110mm) ","个",3]
[16,"PVC-U90°弯头(DN90mm) ","个",21]
[17,"PVC-U90°弯头(DN110mm) ","个",6]
[18,"阀门井","座",84]
[19,"支管控制阀(铸铁碟阀DN63mm)","个",84]
[20,"泄水井","座",84]
[21,"泄水阀(铸铁碟阀DN63mm)","个",84]
[22,"球阀井","座",406]
[23,"PE球阀(DN50mm)","个",442]
[24,"PE球阀(DN32mm)","个",735]
[25,"PE90°弯头(DN50mm)","个",442]
[26,"PE正三通(DN50mm)","个",442]
[27,"PVC-U异径三通(DN63-50mm)","个",442]
[28,"PVC-U异径三通(DN63-32mm)","个",735]
[29,"PVC-U内螺纹接头(DN50mm×1\")","个",884]
[30,"PVC-U内螺纹接头(DN32mm×1\")","个",735]
[31,"PE快接外螺纹接头(DN50mm×1\")","个",884]
[32,"PE快接外螺纹接头(DN32mm×1\")","个",735]
[33,"PE快接堵头(DN50mm)","个",884]
[34,"PE快接异径三通(DN50-25mm)","个",2763]
[35,"PE堵头(DN25mm)","个",2763]
[36,"稳流器(10L/h)","个",138325]
[37,"支墩","个",63]
[38,"镇墩","个",335]
[39,"过沟","处",11]
[40,"过路","处",56]
[41,"主管道试压","项",1,null,null,"总价"]
["四","机电设备购置及安装工程"]
[1,"200QJ20-54/4潜水泵及电机","台套",10,null,null,"含配套电缆"]
[2,"150QJ25-56/7潜水泵及电机","台套",5,null,null,"含配套电缆"]
[3,"4吋离心式过滤器+4吋网式过滤器","台套",15]
[4,"一体化钢制施肥罐(100L)","台套",15]
[5,"变频恒压开关柜COCON-PU5.5DV","台套",10]
[6,"变频恒压开关柜COCON-PU7.5DV","台套",5]
[7,"控制电缆(KVVR-450/750V-8*1)","m",{"v":1200,"d":"1200.00"}]
[8,"低压电缆(YJV-0.6/1KV-5*6)","m",{"v":300,"d":"300.00"}]
["五","临时工程"]
["1","施工房屋工程","项",1,null,null,"总价"]
["2","其他临时工程","项",1,null,null,"总价"]
["六","安全文明措施费","项",1,{"v":20000,"d":"20000.00"},null,"总价"]
["七","备用金","项",1,{"v":30000,"d":"30000.00"},null,"总价"]
["合计"]
[]
["投标人：",{"$nulls":5},"(盖章)"]
["法定代表人或委托代理人：",{"$nulls":5},"(签字)"]
[{"$nulls":3},"             年             月             日"]